## Weekly KPI
Dhanflow — Weekly KPI Report
Week: 25 May — 31 May 2026
Metric | This Week | Last Week | Change
Total Applications | 1 | 3 | -2
Total Disbursed | 1 | 2 | -1
Total Amount Disbursed | 140000 | 260000 | -120000
Rejections | 0 | 1 | -1
Overdue Repayments | 5 | 3 | 2
KYC Pass Rate | 80% | 75% | 5%

## Status Report
Dhanflow — Weekly Status Report
Week: 25 May — 31 May 2026
Task | Owner | Status | Due Date | Comments
Loan Application Flow | Engineering | ✅ Done | 2026-06-14 | Completed on time
KYC Aadhaar Integration | Engineering | 🔄 In Progress | 2026-06-14 | 80% complete
KYC PAN Integration | Engineering | 🔄 In Progress | 2026-06-14 | 70% complete
Credit Scoring Model | Product | 🔄 In Progress | 2026-06-14 | Under review
Loan Approval Workflow | Product | 🔄 In Progress | 2026-06-14 | Pending sign off
Bank Transfer API | Engineering | ⏳ To Do | 2026-06-14 | Starts next week
EMI Repayment Tracker | Engineering | ⏳ To Do | 2026-06-14 | Dependency on API
Repayment Dashboard | Product | ⏳ To Do | 2026-06-14 | Design pending
Overdue Repayment Logic | Engineering | 🚨 Blocked | 2026-06-14 | Waiting for business rules
Program Documentation | PM Intern | 🔄 In Progress | 2026-06-14 | 60% complete
Status | Count
Done | 1
In Progress | 5
To Do | 3
Blocked | 1

## Risk Log
Dhanflow — Risk Log
Week: 25 May — 31 May 2026
Risk ID | Risk Description | Category | Probability | Impact | Risk Level | Mitigation Plan | Owner | Status
R001 | Aadhaar API delay from vendor | Technical | High | High | 🔴 Critical | Identify backup KYC vendor | Engineering Lead | Open
R002 | Low credit score borrowers applying | Business | High | Medium | 🟠 High | Tighten eligibility criteria | Product Manager | Open
R003 | Bank transfer API integration delay | Technical | Medium | High | 🟠 High | Start parallel testing early | Engineering Lead | Open
R004 | Overdue repayments increasing | Financial | High | High | 🔴 Critical | Send reminders 3 days before due date | Business Team | In Progress
R005 | KYC failure rate above 20% | Compliance | Medium | High | 🟠 High | Add clearer KYC instructions in app | Product Manager | Open
R006 | Sprint delivery delay | Program | Low | Medium | 🟡 Medium | Daily standups to track progress | PM Intern | Open
R007 | Incomplete documentation | Program | Low | Low | 🟢 Low | Allocate 1 hour daily for docs | PM Intern | Open
Risk Level | Count
Critical | 2
High | 3
Medium | 1
Low | 1

## Trend Tracker
Dhanflow — Weekly Trend Tracker
January 2026 — May 2026
Month | Total Applications | Total Amount | Disbursed | Rejected | Pending | Disbursement Rate
2026-01-01 | 4 | 250000 | 3 | 1 | 0 | 75%
2026-02-01 | 4 | 300000 | 3 | 1 | 0 | 75%
2026-03-01 | 3 | 350000 | 2 | 0 | 1 | 67%
2026-04-01 | 3 | 370000 | 2 | 1 | 1 | 67%
2026-05-01 | 1 | 140000 | 1 | 0 | 0 | 100%

## Dashboard
Dhanflow — Weekly Ops Dashboard
Total Apps | Disbursed | Rejected | Overdue | KYC Pass Rate
1 | 1 | 0 | 5 | 80%